## Sheet1
Sr .No | Date | Task | Names | Due date | Conclusion | Pendings
1 | 2026-06-30 | 1.project discussion 2.implementation strategy | Sandip | 2026-05-31 | OTA bootloader, Roolabck and recovery ,contact neel madhav at 6JUN | Multi partitining , secure boot chain Delta patches ,
Abhijeet
chetan
tejas
Aditya
2 | 2026-06-02 | 1.how to connect multiple Nodes like stm & beagle bone 2.finalize objectives.xls 3.AWS when IOT starts 4.prepare git repo | Sandip | 2026-06-03 | Project Title:- Secure OTA Firmware Management System for RTOS-Based ECU Networks
Abhijeet
chetan
tejas
Aditya
3 | 2026-06-05 |  | Sandip |  | 1. flow :- CAN Network → BeagleBone Linux → IoT Dashboard →FreeRTOS → UART Communication → Flash Programming → Bootloader → OTA Protocol → Security → System Testing
Abhijeet
chetan
tejas
Aditya
4 |  |  | Sandip
Abhijeet
chetan
tejas
Aditya
Sandip
Abhijeet
chetan
tejas
Aditya

## Sheet2
Sr. No |  | Objectives | Status
1 |  | Hardware and Software interface Stm32 and Beagle Bone CAN network | not started | completed
| 1 | can interface
2 |  | Bootloaders for Stm32 | not started | in progress
3 |  | BeagleBone Black Linux Gateway OTA Server Agent | not started | not started
4 |  | IoT Dashboard aws | not started